## SprintＸ
| SprintＸ |  |  |  |  | Top: Losses of working time (half days, time off, training, departmental measures, work outside the project, etc.)
Start: | 2019-01-07 |  |  |  |  | Bottom: Development hours (enter a "-" for days when each team member is not working)
[5 empty] | SM | Development team
|  |  | Regular events/meetings | Hours |  | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7 | Total | Remaining | Notes
| 2019-01-07 | Mon
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 490
| 2019-01-08 | Tue
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 455
| 2019-01-09 | Wed
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 420
| 2019-01-10 | Thu
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 385
| 2019-01-11 | Fri
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 350
| 2019-01-12 | Sat
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 315
| 2019-01-13 | Sun
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 280
| 2019-01-14 | Mon
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 245
| 2019-01-15 | Tue
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 210
| 2019-01-16 | Wed
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 175
| 2019-01-17 | Thu
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 140
| 2019-01-18 | Fri
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 105
| 2019-01-19 | Sat
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 70
| 2019-01-20 | Sun
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 35
[6 empty] | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 490
[6 empty] | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7
[5 empty] | 2019-01-07 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 490
[5 empty] | 2019-01-08 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 455
[5 empty] | 2019-01-09 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 420
[5 empty] | 2019-01-10 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 385
[5 empty] | 2019-01-11 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 350
[5 empty] | 2019-01-12 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 315
[5 empty] | 2019-01-13 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 280
[5 empty] | 2019-01-14 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 245
[5 empty] | 2019-01-15 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 210
[5 empty] | 2019-01-16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 175
[5 empty] | 2019-01-17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 140
[5 empty] | 2019-01-18 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 105
[5 empty] | 2019-01-19 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
[5 empty] | 2019-01-20 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35
|  |  |  | Remaining hours per day | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Work by systems manager or leader | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Other work (emails, general tasks, meetings) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
[5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
The green areas are calculated automatically
Note on B2: Enter start date of sprint
Note on E5: Enter with a minus sign (include travel time)
Note on G5: Overwrite with names of personnel

## Sprint1
| Sprint1 |  |  |  |  | Top: Losses of working time (half days, time off, training, departmental measures, work outside the project, etc.)
Start: | 2019-01-07 |  |  |  |  | Bottom: Development hours (enter a "-" for days when each team member is not working)
EXAMPLE
[5 empty] | SM | Development team
|  |  | Regular events/meetings | Hours |  | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7 | Total | Remaining | Notes
| 2019-01-07 | Mon | Sprint planning/prep. | -6
|  |  | Retrospective |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168
| 2019-01-08 | Tue | Planning and Decomposing Task | -6
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168
| 2019-01-09 | Wed |  |  |  | -4 | [8 empty] | Member 1 1/2 day -4.0
[5 empty] | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 31 | 168
| 2019-01-10 | Thu
[5 empty] | 5 | 5 | - | 5 | 5 | 5 | 5 | 5 | 30 | 137 | Member 2 time off
| 2019-01-11 | Fri
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 107
| 2019-01-12 | Sat
[5 empty] | - | - | - | - | - | - | - | - | 0 | 72
| 2019-01-13 | Sun
[5 empty] | - | - | - | - | - | - | - | - | 0 | 72
| 2019-01-14 | Mon
|  |  | Public holiday (Coming-of-Age Day) |  | - | - | - | - | - | - | - | - | 0 | 72
| 2019-01-15 | Tue | [5 empty] | -4 | [6 empty] | Member 3 training -4.0
[5 empty] | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 31 | 72
| 2019-01-16 | Wed | Refinement | -4
[5 empty] | 1 | 1 | 1 | 1 | - | 1 | 1 | 1 | 6 | 41 | Member 4 back at office
| 2019-01-17 | Thu
[5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35 | 35
| 2019-01-18 | Fri | Sprint review/prep. | -6
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2019-01-19 | Sat
[5 empty] | - | - | - | - | - | - | - | - | 0 | 0
| 2019-01-20 | Sun
[5 empty] | - | - | - | - | - | - | - | - | 0 | 0
[6 empty] | 22 | 21 | 22 | 25 | 26 | 26 | 26 | 168
[6 empty] | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7
[5 empty] | 2019-01-07 | 22 | 21 | 22 | 25 | 26 | 26 | 26 | 168
[5 empty] | 2019-01-08 | 22 | 21 | 22 | 25 | 26 | 26 | 26 | 168
[5 empty] | 2019-01-09 | 22 | 21 | 22 | 25 | 26 | 26 | 26 | 168
[5 empty] | 2019-01-10 | 21 | 16 | 17 | 20 | 21 | 21 | 21 | 137
[5 empty] | 2019-01-11 | 16 | 16 | 12 | 15 | 16 | 16 | 16 | 107
[5 empty] | 2019-01-12 | 11 | 11 | 7 | 10 | 11 | 11 | 11 | 72
[5 empty] | 2019-01-13 | 11 | 11 | 7 | 10 | 11 | 11 | 11 | 72
[5 empty] | 2019-01-14 | 11 | 11 | 7 | 10 | 11 | 11 | 11 | 72
[5 empty] | 2019-01-15 | 11 | 11 | 7 | 10 | 11 | 11 | 11 | 72
[5 empty] | 2019-01-16 | 6 | 6 | 6 | 5 | 6 | 6 | 6 | 41
[5 empty] | 2019-01-17 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 35
[5 empty] | 2019-01-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2019-01-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2019-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining hours per day | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Work by systems manager or leader | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Other work (emails, general tasks, meetings) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
[5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
The green areas are calculated automatically
Note on B2: Enter start date of sprint
Note on E5: Enter with a minus sign (include travel time)
Note on G5: Overwrite with names of personnel
Note on G10: Enter with a minus sign
Note on H13: Use a minus sign for days when a member is not working.
Note on I22: Enter with a minus sign
Note on J25: Use a minus sign for days when a member is not working.